## Read Me
Document Title | RCL-RVM-CMQA1 Rascal Requiremetns Verification Matrix
Document Author | Tom Moline
Approved By | Nate Richard
Revision | -
Last Edit Date | 2013-11-04
Nomenclature
Shorthand | Longform
I&T | Integration and Testing
PD | Preliminary Design
Document Summary
This document consists of the Requirments Verification Matrix for various mission configurations of the Rascal Spacecraft. Each tab on the bottom of the page contains a separate RVM for each of said mission configurations. Regardless of the mission, each requirment listed in the RVM is defined relative to a specific phase of the mission (Integration and Testing, On-Orbit, Preliminary Design) and to a specific method of verification (Test, Analysis, Demo, Examine).
Testing verification consists of subjecting a particular design to vibration or functional testing, as needed. Analytical verification consists of FEM analysis of structural components, thermal modeling, orbit calculations, etc. Demo verification consists of demonstrating functionality outside of the context of teting. Examination verification consists of measurements and visual inspections.

## 1 Active-1 Passive
Mission Phase | Subsystem | Requirement | Relevent Document | Verification Method |  |  |  | Verification Artifact | Task Number
|  |  |  | Test | Analysis | Demo | Examine
Stage 1: Pre-Mission Preliminary Design/Integration and Testing
I&T | Structures | Center of gravity shall be located withina sphere of 2 cm of the geometric center | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM1
I&T | Structures | No external components other than the CubeSat rails may make contact with the deployer | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM2
I&T | Structures | Shall incorporate a Remove Before Flight pin | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM3
I&T | Structures | Shall incorporate a deployment switch | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM4
I&T | Structures | Mass shall not exceed 8.0 kg | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM5
I&T | Structures | No Protrusion shall extend beyond 6.5 mm normal to any external surface | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM6
PD | Structures | The CubeSat coordinate system shall be defined as specifed in Figure 1 | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM7
I&T | Structures | The ends of the rails on the +Z/-Z faces shall have a minimum surface area of 6.5 mm x 6.5 mm | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM8
I&T | Structures | The +Y/-Y Faces of any CubeSat structure shall have a length of 100 mm | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM9
PD | Structures | All materials used in the CubeSat shall have a Total Mass Loss of less than 1.0% (List of Low Outgassing Materials available at outgassing.nasa.gov) | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM10
PD | Structures | All materials used in the CubeSat shall have a Collected Volatile Condensable material of less than 0.1% | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM11
PD | Structures | Pressure Vessals shall have a factor of safelty no less than 4 | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM12
PD | Mission Operations | CubeSat must be in orbit for at least 6 months | Team Bravo RFP |  | x |  |  |  | RCL-MOP-RVM1
PD | Mission Operations | CubeSat must deorbit within 25 years of being launched | Process for Limiting Orbital Debris (NASA-STD-8719.14A) |  | x |  |  |  | RCL-MOP-RVM2
I&T | Testing | CubeSat must survive Random Vibration Testing relative to the NASA GEVS Qualification Profile (Shown in Figure 2) | General Environmental Verification Standard for GSFC Flight Prgrams and Projects (GSFC-STD-7000A) | x |  |  |  |  | RCL-TST-RVM1
I&T | Testing | CubeSat shall be subjected to a temperatue of 60 ⁰C at a pressure of 1x10^-4 Torr for at least 6 hours | Past ELaNa CubeSat-P-POD ICD's | x |  |  |  |  | RCL-TST-RVM2
PD | Thermal | All CubeSat components shall be rated to withstand a temperature range between -20 ⁰C and 70 ⁰C | Team Bravo RFP |  | x |  |  |  | RCL-THM-RVM1
Stage 2: Mission Success Criterea
RCL-S-RVM18
RCL-S-RVM19
RCL-S-RVM20
RCL-S-RVM21
RCL-S-RVM22
RCL-S-RVM23
RCL-S-RVM24
RCL-S-RVM25
RCL-S-RVM26
RCL-S-RVM27
RCL-S-RVM28
RCL-S-RVM29
RCL-S-RVM30
RCL-S-RVM31
RCL-S-RVM32
RCL-S-RVM33
RCL-S-RVM34
RCL-S-RVM35
RCL-S-RVM36

## Both Active
Mission Phase | Subsystem | Requirement | Relevent Document | Verification Method |  |  |  | Verification Artifact | Task Number
|  |  |  | Test | Analysis | Demo | Examine
Stage 1: Pre-Mission Preliminary Design/Integration and Testing
I&T | Structures | Center of gravity shall be located withina sphere of 2 cm of the geometric center | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM1
I&T | Structures | No external components other than the CubeSat rails may make contact with the deployer | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM2
I&T | Structures | Shall incorporate a Remove Before Flight pin | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM3
I&T | Structures | Shall incorporate a deployment switch | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM4
I&T | Structures | Mass shall not exceed 8.0 kg | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM5
I&T | Structures | No Protrusion shall extend beyond 6.5 mm normal to any external surface | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM6
PD | Structures | The CubeSat coordinate system shall be defined as specifed in Figure 1 | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM7
I&T | Structures | The ends of the rails on the +Z/-Z faces shall have a minimum surface area of 6.5 mm x 6.5 mm | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM8
I&T | Structures | The +Y/-Y Faces of any CubeSat structure shall have a length of 100 mm | CubeSat Design Specification Rev 12 |  |  |  | x |  | RCL-STR-RVM9
PD | Structures | All materials used in the CubeSat shall have a Total Mass Loss of less than 1.0% (List of Low Outgassing Materials available at outgassing.nasa.gov) | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM10
PD | Structures | All materials used in the CubeSat shall have a Collected Volatile Condensable material of less than 0.1% | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM11
PD | Structures | Pressure Vessals shall have a factor of safelty no less than 4 | CubeSat Design Specification Rev 12 |  | x |  |  |  | RCL-STR-RVM12
PD | Mission Operations | CubeSat must be in orbit for at least 6 months | Team Bravo RFP |  | x |  |  |  | RCL-MOP-RVM1
PD | Mission Operations | CubeSat must deorbit within 25 years of being launched | Process for Limiting Orbital Debris (NASA-STD-8719.14A) |  | x |  |  |  | RCL-MOP-RVM2
I&T | Testing | CubeSat must survive Random Vibration Testing relative to the NASA GEVS Qualification Profile (Shown in Figure 2) | General Environmental Verification Standard for GSFC Flight Prgrams and Projects (GSFC-STD-7000A) | x |  |  |  |  | RCL-TST-RVM1
I&T | Testing | CubeSat shall be subjected to a temperatue of 60 ⁰C at a pressure of 1x10^-4 Torr for at least 6 hours | Past ELaNa CubeSat-P-POD ICD's | x |  |  |  |  | RCL-TST-RVM2
I&T | Testing | Full CubeSat System shall be able to execute all commands associtated with its operation over RF | Environmental Testing Requiremnts | x |  |  |  |  | RCL-TST-RVM3
I&T | Testing | Full CubeSat System shall be able to close a link with the SSRL Ground Station from a distance of at least 200 meters | Environmental Testing Requiremnts | x |  |  |  |  | RCL-TST-RVM4
I&T | Testing | Full CubeSat System shall be able to document the functionality of each subsystem through the running of a full-functional test | Environmental Testing Requiremnts | x |  |  |  |  | RCL-TST-RVM5
PD | Thermal | All CubeSat components shall be rated to withstand a temperature range between -20 ⁰C and 70 ⁰C | Team Bravo RFP |  | x |  |  |  | RCL-THM-RVM1
Stage 2: Mission Success Criterea
On-Orbit | [8 empty] | RCL-S-RVM18
On-Orbit | [8 empty] | RCL-S-RVM19
On-Orbit | [8 empty] | RCL-S-RVM20
On-Orbit | [8 empty] | RCL-S-RVM21
On-Orbit | [8 empty] | RCL-S-RVM22
On-Orbit | [8 empty] | RCL-S-RVM23
On-Orbit | [8 empty] | RCL-S-RVM24
On-Orbit | [8 empty] | RCL-S-RVM25
On-Orbit | [8 empty] | RCL-S-RVM26
On-Orbit | [8 empty] | RCL-S-RVM27
On-Orbit | [8 empty] | RCL-S-RVM28
On-Orbit | [8 empty] | RCL-S-RVM29
On-Orbit | [8 empty] | RCL-S-RVM30
On-Orbit | [8 empty] | RCL-S-RVM31
On-Orbit | [8 empty] | RCL-S-RVM32
On-Orbit | [8 empty] | RCL-S-RVM33
On-Orbit | [8 empty] | RCL-S-RVM34
On-Orbit | [8 empty] | RCL-S-RVM35
On-Orbit | [8 empty] | RCL-S-RVM36

## Figure 1-Coordinate System
Figure 1- CubeSat Coordinate System

## Figure 2- NASA Gevs
Figure 2- NASA GEVS Random Vibration Profile